## Phase 8 Acceptance Audit
section | check | result | severity | detail | location | fix_status
1-Mission Control | 6/6 missions exist | PASS | OK | All 6 missions active: Dog Food Authority, Dog Harness Commercial, Pet Insurance Trust, Cat Toys Recovery, Homepage Engagement, AI Search Adaptation | API: /api/mission-control/missions | N/A
1-Mission Control | Pet Insurance target_cluster = pet_insurance | PASS (FIXED) | CRITICAL | Was pet_supplements - corrected to pet_insurance in mission_control.json | mission_control.json > mis_pet_insurance_trust > target_cluster | Fixed this session
1-Mission Control | 65 backlog items visible | PASS | OK | 65 items confirmed via /api/mission-control/backlog | API: /api/mission-control/backlog | N/A
1-Mission Control | Backlog synced to WP draft IDs | FAIL | MEDIUM | 0/65 backlog items have wp_draft_id field populated. Drafts exist in WP (3715/3717/3719/3720/3722) but backlog entries not linked. | API: /api/mission-control/backlog - wp_draft_id field | Needs fix
1-Mission Control | Dog Food drafts show preview URLs | FAIL | MEDIUM | No preview_url in backlog entries. WP preview URLs exist (e.g. ?page_id=3715) but not synced to backlog data. | API: /api/mission-control/backlog - preview_url field | Needs fix
1-Mission Control | Missions show progress/confidence/labels | PASS | OK | All missions show: progress_pct, confidence_pct, data_source_label (MODELLED FORECAST), data_maturity, last_validation_date, responsible_agents, milestones, next_recommended_action | API: /api/mission-control/missions | N/A
2-Dog Food | 4 drafts exist in WP | PASS | OK | Pages 3715 (Hub 3936w), 3717 (Dry 338w), 3719 (DryVsWet 310w), 3720 (Puppy 306w) all confirmed draft status | WordPress REST API | N/A
2-Dog Food | Draft IDs and preview URLs visible | FAIL | MEDIUM | Draft IDs exist in WP but NOT linked in mission backlog or mission data. No preview_url field in backlog items. | Mission Control backlog | Needs sync script
2-Dog Food | Product Evidence linked to register | PASS | OK | 10 entries in register, all linked to draft page IDs (3715/3717/3719/3720) | /opt/pethub-agents/shared/data/product_evidence_register.json | N/A
2-Dog Food | Content QA scores visible | PASS | OK | QA scores: Hub 10/10, Dry 6/10, DryVsWet 7/10, Puppy 7/10. All pass filler/fake checks. | Phase8_Draft_QA.csv | N/A
2-Dog Food | Metadata/schema/linking proposals visible | PASS | OK | Schema proposals: Hub (Article+ItemList+FAQPage+BreadcrumbList), others (Article+BreadcrumbList). Internal linking proposals documented. | schema_proposals.json + Phase8_Draft_QA.csv | N/A
3-Pet Insurance | RED gated | PASS | OK | approval_status = red_flag confirmed. Next action: Await red-flag approval from business owner. | API: /api/mission-control/missions | N/A
3-Pet Insurance | Target cluster = pet_insurance | PASS (FIXED) | CRITICAL | Was pet_supplements - now corrected to pet_insurance | mission_control.json | Fixed this session
3-Pet Insurance | Methodology/trust draft exists | PASS | OK | Page 3722 exists in WP as draft: Pet Insurance UK - Methodology & Trust Framework | WordPress page_id=3722 | N/A
3-Pet Insurance | Live publishing blocked | PASS | OK | Page 3722 confirmed DRAFT status. WP drafts are not indexable (noindex). approval_status = red_flag. | WordPress + mission_control.json | N/A
3-Pet Insurance | Affiliate links blocked | PASS | OK | 0 affiliate links on insurance page. RED gate check RED-02 confirms. Mission explicitly states NO affiliate links until compliance review. | Phase8_PetInsurance_RED_Gate.csv RED-02 | N/A
3-Pet Insurance | Visible approval queue item | PARTIAL | LOW | approval_status=red_flag visible in mission data. No separate approval queue endpoint - status tracked in mission itself. | API: /api/mission-control/missions | Consider dedicated approval queue
4-CoPilot | show active missions | PASS | OK | Returns all 6 missions with status/progress/confidence. Read-only. | API: /api/copilot/ask | N/A
4-CoPilot | what mission matters most? | PASS | OK | Returns Dog Food Authority Expansion (highest priority, 78.5% confidence). Read-only. | API: /api/copilot/ask | N/A
4-CoPilot | what should we publish next? | PASS (FIXED) | CRITICAL | Was recommending Dog Insurance UK Brief from RED-gated mission. Now filters out red_flag missions. Returns Harness Product Schema instead. | copilot_mission_commands.py _handle_next_publish | Fixed this session
4-CoPilot | what is blocking Dog Food authority? | PASS | OK | Returns 5 pending milestones correctly. Read-only. | API: /api/copilot/ask | N/A
4-CoPilot | what content does Dog Food mission need? | PASS | OK | Returns 8 content assets + 4 evidence assets correctly. | API: /api/copilot/ask | N/A
4-CoPilot | create next action plan | PASS | OK | Returns prioritised plan. Pet Insurance correctly shows 'Await red-flag approval'. Read-only. | API: /api/copilot/ask | N/A
4-CoPilot | summarize mission progress | PASS | OK | Returns all 6 missions with avg progress 11.8%, avg confidence 65.2%. Read-only. | API: /api/copilot/ask | N/A
5-Social | Facebook status | PASS | OK | AMBER, autonomy_level=3, api_health=not_connected (token in config but FB Graph API not actively tested), can_auto_post=false, approval_required=true, retry_queue=0 | API port 8103: /api/social/channels/facebook | N/A
5-Social | Instagram status | PASS | OK | RED, autonomy_level=2, api_health=degraded_meta_review_pending, status=degraded, auto-posting blocked, approval_required=true | API port 8103: /api/social/channels/instagram | N/A
5-Social | TikTok status | PASS | OK | RED, not_connected, drafts and scripts only, auto-posting blocked | API port 8103: /api/social/channels/tiktok | N/A
5-Social | Pinterest status | PASS | OK | RED, not_connected, pin drafts only, auto-posting blocked | API port 8103: /api/social/channels/pinterest | N/A
5-Social | YouTube status | PASS | OK | RED, not_connected, scripts and briefs only, auto-posting blocked | API port 8103: /api/social/channels/youtube_shorts | N/A
5-Social | Last successful post per channel | INFO | LOW | All channels: last_successful_post = null. No posts have been made yet. | API port 8103: /api/social/channels | Expected - channels not fully connected
5-Social | Retry queue | PASS | OK | 0 pending, 0 total. Clean queue. | API port 8103: /api/retry-queue | N/A
5-Social | DLQ entries | PASS | OK | 4 entries total: 1 escalated (seo_agent), 2 dismissed (content_agent + social_agent), 1 pending (manager_agent). All from integration testing. | API: /api/dlq/stats | N/A
5-Social | Instagram degraded state | PASS | OK | status=degraded, degraded_reason='Meta API review pending', auto-posting correctly blocked | API port 8103: /api/social/channels/instagram | N/A
5-Social | Auto-posting blocked on degraded | PASS | OK | can_auto_post=false for ALL channels. Facebook blocked due to 'API not connected'. Others blocked due to RED/degraded state. | API port 8103: /api/social/channels/*/can-post | N/A
6-Affiliate | Pages scanned | PASS | OK | 25 pages scanned by affiliate agent | API port 8107: /api/status | N/A
6-Affiliate | Pages with affiliate links | PASS | OK | 15 pages with affiliate links, 142 links found total | API port 8107: /api/status | N/A
6-Affiliate | Pages with disclosure | FAIL | MEDIUM | Agent reports 5/15 pages have disclosure. WP source confirms 17/17 have disclosure div. Agent scan logic not detecting disclosure divs correctly. | API port 8107: /api/compliance vs WordPress source | Agent scan logic needs update
6-Affiliate | Links with rel=sponsored | FAIL | MEDIUM | Agent reports 142 links missing rel=sponsored. WP source HTML confirms all 141 external links DO have rel=sponsored. Agent scan reads WP differently from actual source. | API port 8107: /api/compliance | Agent scan logic needs update
6-Affiliate | Duplicate tracking warning | PASS | OK | No duplicate tracking scripts found (confirmed in WP source scan) | affiliate_source_sample.txt | N/A
7-Product Evidence | Register contains real entries | PASS | OK | 10 real product entries: Royal Canin, James Wellbeloved, Lily's Kitchen, Harringtons, Forthglade, Butcher's, Burns, Orijen etc. | product_evidence_register.json | N/A
7-Product Evidence | Entries linked to Dog Food pages | PASS | OK | All 10 entries linked to Dog Food draft pages (3715/3717/3719/3720). No Cat Toys links (none created yet). | product_evidence_register.json - linked_pages field | N/A
7-Product Evidence | Prices/ratings/stock blocked if unverified | PASS | OK | All 10 entries: evidence_status=partial, approval_status=blocked_pending_evidence, price/rating/stock_verification=not_verified. risk_flags and unverified_claims lists populated. | product_evidence_register.json | N/A
8-NOC | NaN timestamps | PASS | OK | grep found 0 NaN in mission_control.json and dead_letter_queue.json. All timestamps valid ISO 8601. | Direct file grep | N/A
8-NOC | Event bus status | FAIL | LOW | Returns empty {} - no meaningful status data from event bus API | API: /api/events/status | Needs event bus health endpoint
8-NOC | Kill switch status | FAIL | MEDIUM | No /api/kill-switch/status endpoint found on manager agent. Kill switch module exists in code but no API route registered. | Manager agent API | Needs route registration
8-NOC | Recovery drill status | FAIL | LOW | No /api/recovery/status endpoint. Drill was run manually and passed (64ms RTO). | Manager agent API | Consider adding status endpoint
8-NOC | DLQ status | PASS | OK | DLQ API fully functional: stats + entries + lifecycle operations all working. 4 entries with valid statuses. | API: /api/dlq/stats | N/A
8-NOC | PostgreSQL pool status | PASS | OK | PostgreSQL active (systemctl is-active = active) | systemctl status | N/A
8-NOC | Redis status | PASS | OK | Redis responding (PING=PONG), 1.5M memory used | redis-cli ping + info memory | N/A
8-NOC | Google/GSC/GA4 labels | PASS | OK | All missions labelled MODELLED FORECAST. No credentials directory = NOT CONNECTED. Clearly labelled. | mission_control.json + filesystem check | N/A
8-NOC | Contradictory healthy/down states | PASS | OK | No contradictions found. All 9 services active. Social channels correctly show degraded where appropriate. | systemctl + API checks | N/A
8-NOC | Backup status | PARTIAL | HIGH | May 25 backup: OK (766K .gpg file). May 26 03:00 backup: INCOMPLETE (log shows only 2 steps, no .gpg file, staging dir left over). Manual backup also fails (permission denied on live_intelligence.json). | /opt/pethub-agents/backups/ | Needs backup script permission fix